## Asset Inventory
Asset ID | Asset Name | Asset Type | Owner | Confidentiality | Integrity | Availability
A1 | Client Case Files | Data | Legal Dept | High | High | Medium
A2 | Billing System | Application | Finance Dept | Medium | High | Medium
A3 | Document Management System | Application | IT Dept | High | High | High
A4 | HR Records | Data | HR Dept | High | Medium | Medium
A5 | Email System (MS 365) | Service | IT Dept | High | Medium | High
A6 | Attorney Laptops | Hardware | IT Dept | High | Medium | Medium
A7 | VPN Access | Network Service | IT Dept | High | High | High

## Risk Identification
Risk ID | Asset | Threat | Vulnerability | Potential Impact
R1 | Client Case Files | Ransomware | No offline backups | Data loss; confidentiality breach
R2 | Email System | Phishing | No MFA; weak training | Credential theft; data exposure
R3 | Attorney Laptops | Device Theft | No encryption | Unauthorized data access
R4 | DMS | Insider Threat | Excessive permissions | Unauthorized access
R5 | VPN | Brute-force Attack | Weak password policy | Unauthorized network access
R6 | HR Records | Data Breach | Misconfigured permissions | PII exposure
R7 | Billing System | System Downtime | No redundancy | Billing disruption

## Risk Assessment
Risk ID | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level
R1 | 4 | 5 | 20 | Critical
R2 | 4 | 4 | 16 | High
R3 | 3 | 5 | 15 | High
R4 | 3 | 4 | 12 | Medium
R5 | 2 | 5 | 10 | Medium
R6 | 3 | 3 | 9 | Medium
R7 | 2 | 3 | 6 | Low

## Risk Treatment Plan
Risk ID | Mitigation Strategy | Control Type | NIST Mapping | Owner | Status
R1 | Offline + cloud backups; EDR | Technical | CP-9, SI-3 | IT Director | In Progress
R2 | MFA; phishing simulations | Admin/Tech | IA-2, AT-2 | IT Sec Lead | Planned
R3 | Full-disk encryption; remote wipe | Technical | MP-5 | IT Director | Complete
R4 | Least privilege; access reviews | Administrative | AC-2 | Ops Manager | In Progress
R5 | Strong password policy; lockout | Technical | IA-5 | Net Admin | Planned
R6 | Improve HR permissions | Admin/Tech | AC-6 | HR Manager | Planned
R7 | Redundancy + failover | Technical | CP-10 | Infra Lead | In Progress

## Executive Summary
Executive Summary
Top risks identified include ransomware (R1), phishing (R2), and endpoint data exposure (R3). Recommended controls include MFA, encryption, EDR, and strong backup processes. Quarterly access reviews and continuous monitoring are advised.

## Heatmap Data
Risk ID | Likelihood | Impact | Risk Score
R1 | 4 | 5 | 20
R2 | 4 | 4 | 16
R3 | 3 | 5 | 15
R4 | 3 | 4 | 12
R5 | 2 | 5 | 10
R6 | 3 | 3 | 9
R7 | 2 | 3 | 6